# **Refreshing Te Marautanga o Aotearoa**

## **Indicative timeline (2021-2025)**

# This narrative identifies indicative timelines for the different work programmes within the refresh of Te Marautanga o Aotearoa. Where appropriate, timeline entries are shown as part of these work streams: Māori-centred Design (MCD); Testing (TEST); Implementation (IMP); and Announcements (ANN).

Three values are a focus throughout this indicative timeline: trust, coherence and equity.

**2018**

(TEST) Kōrero Mātauranga – Community Wānanga.

**2019**

(MCD) Curriculum, Progress and Achievement Ministerial Advisory Group (CPA MAG) Report 2019 – includes principles of Trust, Coherence and Equity.

**2020**

(MCD) Ohu Matua established – testing He Tamaiti Hei Raukura and 4 Cab report directives.

**2021**

**February 2021**

(ANN) Minister announces the refresh of *Te Marautanga o Aotearoa.*

**March 2021**

(MCD) Rōpū Whāiti established (refresh of *Te Marautanga o Aotearoa*)

Māori-centred design approach confirmed.

**September 2021**

(ANN) Te Takanga o Te Wā Gazetted.

**May 2021**

(MCD) Rōpū Rautaki established (te reo matatini and pāngarau strategy).

(TEST) Te Takanga o Te Wā in-class testing.

**June 2021**

(IMP) Te Takanga o Te Wā implementation planning.

**July 2021**

(MCD) Te Takanga o Te Wā engagements; Whakarongo – Engagements with Kura.

**September 2021**

(MCD) Kōrero – National Hui refresh curriculum.

(TEST) Trial He Tīrewa Ako.

**2022**

**February 2022**

(MCD) Wānanga focus on curriculum framing.

(TEST) Trial Te Tīrewa Mātai.

(IMP) Te Takanga o Te Wā implementation.

**June 2022**

(MCD) Agreed framework and structure.

(IMP) Te Tīrewa Mātai implementation.

**September 2022**

(MCD) Kōrero framework and structure.

**October 2022**

(IMP) Te Tīrewa Mātai implementation.

**November 2022**

(MCD) Wānanga design of supporting material.

**2023**

**February 2023**

(IMP) Implementation design for *Te Marautanga o Aotearoa refresh.*

**June 2023**

(IMP) Kura supported for 2024 implementation.

**2024**

**All 2024**

(IMP) Ongoing kura support.

**February 2024**

(IMP) Kura begin to implement refreshed *Te Marautanga o Aotearoa.*

**2025**

**February 2025**

(IMP) All kura begin to transition to refreshed *Te Marautanga o Aotearoa.*

**October 2025**

(ANN)*Te Marautanga o Aotearoa* Gazetted.

ENDS