# Refreshing Te Marautanga o Aotearoa

## Indicative timeline (2021-2025)

# This narrative identifies indicative timelines for the different work programmes within the refresh of Te Marautanga o Aotearoa.  Where appropriate, timeline entries are shown as part of these work streams: Māori-centred Design (MCD); Testing (TEST); Implementation (IMP); and Announcements (ANN).

Three values are a focus throughout this indicative timeline: trust, coherence and equity.

2018

(TEST) Kōrero Mātauranga – Community Wānanga.

2019

(MCD) Curriculum, Progress and Achievement Ministerial Advisory Group (CPA MAG) Report 2019 – includes principles of Trust, Coherence and Equity.

2020

(MCD) Ohu Matua established – testing He Tamaiti Hei Raukura and 4 Cab report directives.

2021

February 2021

(ANN) Minister announces the refresh of Te Marautanga o Aotearoa.

March 2021

(MCD) Rōpū Whāiti established (refresh of Te Marautanga o Aotearoa)

Māori-centred design approach confirmed.

September 2021

(ANN) Te Takanga o Te Wā Gazetted.

May 2021

(MCD) Rōpū Rautaki established (te reo matatini and pāngarau strategy).

(TEST) Te Takanga o Te Wā in-class testing.

June 2021

(IMP) Te Takanga o Te Wā implementation planning.

July 2021

(MCD) Te Takanga o Te Wā engagements; Whakarongo – Engagements with Kura.

September 2021

(MCD) Kōrero – National Hui refresh curriculum.

(TEST) Trial He Tīrewa Ako.

2022

February 2022

(MCD) Wānanga focus on curriculum framing.

(TEST) Trial Te Tīrewa Mātai.

(IMP) Te Takanga o Te Wā implementation.

June 2022

(MCD) Agreed framework and structure.

(IMP) Te Tīrewa Mātai implementation.

September 2022

(MCD) Kōrero framework and structure.

October 2022

(IMP) Te Tīrewa Mātai implementation.

November 2022

(MCD) Wānanga design of supporting material.

2023

February 2023

(IMP) Implementation design for Te Marautanga o Aotearoa refresh.

June 2023

(IMP) Kura supported for 2024 implementation.

2024

All 2024

(IMP) Ongoing kura support.

February 2024

(IMP) Kura begin to implement refreshed Te Marautanga o Aotearoa.

2025

February 2025

(IMP) All kura begin to transition to refreshed Te Marautanga o Aotearoa.

October 2025

(ANN)Te Marautanga o Aotearoa Gazetted.

ENDS